## MANS.
Material Requests For Mansoura Field
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
MANS 01-15	7/1/2014	8/14/2014	Sally	14/Aug/14	Liquid level tapes & depth gauges	QF	17-Aug-14	25/08/2014 / EXT. 28/8/2014	WADICO	3058/2014	25-Sep-14	1140.00 $	CPT Cairo Airport	20-Nov-14	5-Nov-14	*memo sent to field for evaluation on 1/9/2014 & waiting for their reply / field replied & calrifications sent to vendors on 14/9/2014 / *field replied with another calrification & sent to vendor on 21/9/2014 / *under custom clearance
MANS 02-15	18/Jul/14	31/Jul/14	Islam	3/Aug/14	Refilling helium cylinder	DL	3-Aug-14	3-Aug-14	Ultra Pure Gas	2087-2014	3-Aug-14	1500 LE	Vendor place	10-Aug-14	10-Aug-14	Delivered but the cylinder is leaking / Finished
MANS 03-15	10/Jul/14	31/Jul/14	Tarek	3/Aug/14	Spare parts for bilqas deisel generators	D.F.	3-Aug-14	11-Aug-14	MANTRAC	2098/2014	3-Sep-14	4,428 L.E.	At Mansoura Site	1-Oct-14	20-Oct-14	Waiting offer / Waiting del
MANS 04-15	18/Jul/14	14/Aug/14	Yasser	14/Aug/14	Overhead drum lifter	Q.F.	15-Aug-14	20-Aug-14	Apex	3051/2014	25-Aug-14	2,750.00 $	CPT Cairo Airport	12/10/2014 / Ext. 23/10/2014	25-Oct-14
MANS 05-15	17/Jul/14	27/Aug/14	Sally	27/Aug/14	Toshiba toner	QL	1-Sep-14	4-Sep-14	American Group	2109/2014	2-Oct-14	600.00 L.E.	HEAD OFFICE	12-Oct-14	22/10/2014	*mail sent to toshiba to confirm budgetary offer still valid / reminder sent 8/9, 23/9 & 27/9 with no reply / *received at head office on 19/10 & will be sent to field on 21/10
MANS 06-15	29/Aug/14	7/Sep/14	Amira	7/Sep/14	Spare parts for new glycol pumps	Q.F.	8-Sep-14	14/9/2014 / 28/9/2014	techtools	3061/2014	21/10/2014	$4,301.56	c&f cairo airport	1-Feb-15	23/2/2015	* AL moshir asked foe more information so I sent it to eng.fady on 17/9/2014 and waiting for his reply / * on 23/9/2014 I sent the modified request for quotation as fady sent new drawings / *ON 8/10/2014 SENT TO FADY REQUIRED DATA FROM THE VENDOR / * ON 16/10/2014 SENT TO THE OPERATIONS TO EXPAND THE BUDGET / * under customs since 12/2/2015
MANS 07-15	19/Jul/14	23/Sep/14	Amira	24/Sep/14	Spare parts for dikirnis crude oil heater & LPG heater	Q.F.	25/9/2014	2-Oct-14	TECHTOOLS	3066/2014	5-Nov-14	$6,137.08	c&f cairo airport	5-Apr-15	1-Apr-15	* THE CLOSING DATE EXTENDED TO 12/10/2014 / * offers sent for evaluation on 27/10/2014
MANS 08-15	19/Jul/14	24/Sep/14	Yasser	24/Sep/14	Adaptor for fixed choke	D.F.	24-Sep-14	9-Oct-14	GEOil & Gas	3060/2014	21-Oct-14	12,623.00 $	CPT Cairo Airport	7-Dec-14	10-Dec-14	Waiting Technical Evaluation From Fields "Eng. Ahmed Sweilam" / Materials Received on 01/12/2014 & Waiting Final Receiving from Fields.
MANS 09-15			Tarek		Compressor Revamp	D.F.	3-Aug-14	10-Aug-14	Quimex	3055-2014	21-Sep-14	$142,396	CFR Alex Port	3/1/2015 / *Ext: 1-June-2015		* Waiting L/C opening / * L/C opened end of December 2014 / * Items delivered at site and waiting for M.R.R. (Waiting manufacturer to install the valves)
MANS 10-15	9/Dec/14	28/10/2014	Tarek	28/10/2014	Spare parts for new booster compressors	Q.F.	30-Oct-14	11-Nov-14	Techtools / TPCON	3074-2014	23-Dec-14	9,914 $ / - / 6,715 $	CPT Cairo Airport	15-May-15		* Waiting offers / * Waiting for opr dept. to reply on technical evaluation (sent 08-dec-2014) / * Waiting del / * Under custom clearance from 15-May-2015
MANS 11-15	5/Aug/14	9/Oct/14	Islam	9/Oct/14	Spare parts HMI screens at LPG VRU	QF	5-Aug-14	23-Oct-14	Apex	3067-2014	06/11/2014	15,934.70 $	c&f cairo airport	11/3/2015		Awaiting quotations / Awaiting Evaluation / Awaiting delivery / Delivered end of August and a penalty will be applied / Under custom clearance
MANS 12-15	5/Aug/14	3/Sep/14	Amira	3/Sep/14	Sigma control panel	Q.L	8-Sep-14	15/9/2014 / 22/9/2014	شركة تكنولوجيا الهواء المضغوط	2112/2014	13/10/2014	25,662 L.E	Vendor place	20/10/2014	3-Mar-15	* extended the closing date / *on 24/9/2014 offers sent for evaluation / * on 8/10/2014 I asked the vendors to extend the validity up till 14/10/2014 then I will submit the p.o
MANS 13-15	5/Aug/14	24/Sep/14	Sally	24/Sep/14	Clamps	QL	2-Oct-14	14-Oct-14	PLIDCO	3065/2014	11-Feb-14	21536.08 USD	CFR Alex Port	21/12/2014	8/2/2015	memo sent to Operations dept on 24/9/2014 to inform us the tender criteria / Operation minimized the qty to be a qoutation, RFQ sent to vendors / *OFFERS SENT TO FIELD fro evaluation on 15/10/2014 / *email sent to venodr 21-12 to inform the status of the items, items will be shipped 26-12 / *Under custom clearance
MANS 14-15	18/8/2014	27/8/2014	Amira	27/8/2014	helium	q.l	28/8/2014	28/8/2014	Ultra Pure Gas	2095/2014	28/8/2014	1500 l.e	alex.	10-Sep-14	27/10/2014
MANS 15-15	21/Aug/14	27/Aug/14	Yasser	27/Aug/14	Cover for fire extinguishers	Q.L.	27-Aug-14	31-Aug-14	El Wadi El Gedeed	2099/2014	3-Sep-14	12,455.00 L.E.	Cairo Head Office	25-Sep-14	25-Sep-14	Materials Recived At Mans. Fields And Waiting for Final MRR.
MANS 16-15	23/Aug/14	3/Sep/14	Sally	3/Sep/14	Refilling zero air	QL			ULTRA PURE GAS	2100/2014	4-Sep-14	2400.00 L.E.	EX-W	16-Sep-14	19/10/2014	waiting for the check to be ready / *memo sent to mans field 28/9/2014 to pick up the cylinders
MANS 17-15	2/Sep/14	11/Sep/14	Sally	11/Sep/14	REFILLING HYDROGEN cylinder	QL			ULTRA PURE GAS	2105/2014	14-Sep-14	450.00 L.E.	EX-W	21/9/204	7/11/2014	waiting for the check to be ready / *memo sent to mans field 28/9/2014 to pick up the cylinders / *cylinder was technically not accepted 7 waiting for the vendor to replace it
MANS 18-15	27/9/2014	17/11/2014	Amira	17/11/2014	FILTER HOUSING	Q.F.	17/11/2014	24/11/2014	MOSHIR	3075/2014	28/12/2014	7950 $	CFR	7-May-15	12-May-15	* offers sent to the field evaluation on 27/11/2014 / * evaluation received from the field on 8/12/2014 and I sent to the vendors on 11/12/2014 to ask about more data and the closing date will be on 15/12/2014 / * the shipping documents with the arabian co. from 30/4/2015
MANS 19-15	8/Sep/14	11/Sep/14	Tarek	11/Sep/14	Spare Parts for VRU (B) compressor	D.F.			Dresser Rand	3057-2014	15-Sep-14	7,762 $	CPT Cairo Airport	Immediate shipping DHL		Received
MANS 20-15
MANS 21-15
MANS 22-15	17/Sep/14	24/Sep/14	Mahmoud	24/Sep/14	Eye wash	Q.L	28-Sep-14	26-Oct-14	Technical Services Co.	2122/2014	29-Oct-14	13,320 L.E	HEAD OFFICE	28-Dec-14	14-Feb-15	*Awaiting offers / *Awaiting technical evaluation / *Awaiting new offers based on technical dept. requested clarification / *Awaiting delivery / *Supplier extended the delivery time due to christmas holidays
MANS 23-15	21/Sep/14	28/Sep/14	Yasser	28/Sep/14	Tires	Q.L.	28-Sep-14	30-Sep-14	Sabra Sons	2111/2014	8-Oct-14	5,700.00 L.E.	Cairo Head Office	14-Oct-14	20-Oct-14	Waiting Cheque from Finance Dept.
MANS 24-15	29/92014	7/Oct/14	Islam	7/Oct/14	Linear heart detector	QF	7-Aug-14	21-Oct-14	Wadico	2063-2014	27-Oct-14	2970 GBP	CPT Cairo Airport	22-Dec-14	22-Dec-14	Awaiting delivery / Under custom clearance / Awaiting MRR and invoice received / Finished
MANS 25-15	30/Sep/14	7/Oct/14	Mahmoud	7/Oct/14	Analog input module for ESD system	D.O	12-Oct-14	16-Oct-14	Invensys	3062/2014	22-Oct-14	3120 USD	EX-W	14-Jan-15	13-Jan-15	*Awaiting offer / *Awaiting delivery / *Finished
MANS 26-15	10-Aug-14	02-Nov-14	Yasser	2-Nov-2014	Spare parts for accoodation fire alaram system	Q.L.	10-Nov-14	17-Nov-14	ISS.	2139/2014	30-Nov-14	6,225.00 L.E.	Vendor place	14-Dec-14	15-Dec-14
MANS 27-15	10/Jan/14	27/10/2014	Yasser	27/10/2014	Fire fighting foam solution	Q.F.	29-Oct-14	5-Nov-14	SEPEI "Angus Fire"	3070/2014	25-Nov-14	16,279.00 $	CIP Alex Sea port	15-Jan-15	20-Jan-15	Materials Arrived Alex Seaport on 03/01/2015 . / Waiting Finance dept. to Pay the vendor to enable us release the materials since the payment term CAD.
MANS 28-15	11/Jul/14	17/11/2014	Islam	17/11/2014	Pigs required for pipeline	QF	17-Nov-14	3-Dec-14	Girard	3072-2014	17-Dec-14	3865.40 $	CPT Cairo Airport	11-Feb-15	11-Feb-15	Awaiting evaluation / Awaiting delivery / under custom clearance / Finished
MANS 29-15	16/10/2014	22/2/2015	Islam	22/2/2015	S.P. for Air dryer in gas injection plant	QF	2/22/2015	3/8/2015	Techtools	3017-2015	4/6/2015	16743.87 Euro	c&f cairo airport	5/29/2015		Awaiting delivery / Awaiting MRR, Invoice at Bank / Delivered on 29/5/2015 but item no. was wrong / Techtools will send the correct item / Shipping documents of the correct item has been received on 30/8/2015 / Under custom clearance
MANS 30-15	18/10/2015	1/7/2015	Yasser	1/7/2015	Electrical sparepaerts for mansoura field
MANS 31-15	18/10/2014	18/11/2014	Tarek	19/11/2014	S.P. for batra plant new Gas generator	D.F.			MANTRAC	3008/2015	2/12/2015	5,250 $	CIP CAIRO AIRPORT	4/11/2015		* waiting for opr. Dept. to reply on technical evaluation (Sent on 07-dec-2014) / *Waiting del / *Waiting for payment CAD through bank (01-Apr-2015) / * Delivered to field and waiting for M.R.R. (12-May-2015)
MANS 32-15	24/10/2014	29/10/2014	Islam	29/10/2014	FIRE HYDRANT	QL	29-Oct-14	9-Nov-14	Apex	2127-2014	19-Nov-14	10500 LE	Head office	23-Nov-14	23-Nov-14	Awaiting MRR and invoice received / Finished
MANS 33-15	23/10/2014	29/10/2014	Sally	29/10/2014	Refilling helium cylinder	QL			Ultra Pure Gas	2123/2014	29/10/2014	1500.00 L.E.	EX-W	12/11/2014	25/11/2014	memo sent to field to pick up the cylinder from vendor dated 19/11/2014
MANS 34-15	9/11/2014	18/11/2014	Amira	18/11/2014	Spare parts for fire fighting pumps	Q.F.	23/11/2014	29/11/2014 / 7/12/2014 / 16/12/2014	Apex / Moshir	3006/2015 / 3006/2015 sub.1	28/1/2015	$ 1030 / $ 955	CPT Cairo Airport	8/4/2015 / 15/4/2015	25/3/2015 / 29/5/2015	* the vendor asked to extend the cloising date because of the holidays / * on 9/12/2014 we extend the closing date because I don’t have enough offers / * evaluation received from the field on 19/12/2014 and clarification sent to the vendors on 30/12/2014 and waiting for their reply by maximum on 31/12/2014 / * p.o no. 3006/2015 we didn't receive shipping documents up till 4/5/2015 / * shipping documents for 3006/2015 received on 4/5/2015
MANS 35-15	28/10/2014	2/11/14	AMIRA	2/11/14	Condensate injction microsyrings	q.l	11/3/2014 / 17/11/2014	11/10/2014 / 20/11/2014	unitrade	2147/2014	16/12/2014	3750 l.e	Vendor place	10-Feb-14		* THE CLOSING DATE EXTENDED BECAUSE WE ONLY HAVE ONE OFFER / * the offers sent to the field for evaluation on 30/11/2014 / *evaluation sent from the field on 9/12/2014 then I sent to the vendors to enhance the delivery / * received 2 each out of 3 on 17/2/2015
MANS 36-15	30/10/2014	5/11/14	Mahmoud	5/11/14	American Window Envelope	Q.L	9-Nov-14	11-Nov-14	Macy Envelope	2126/2014	11-Nov-14	882 L.E	HEAD OFFICE	18-Nov-14	17-Nov-14	*Awaiting offers / *Awaiting delivery / *Materials received at head office on 13/11/2014
MANS 37-15	12/11/2014	18/11/2014	Islam	18/11/2014	Spare parts for forklift in south batra plant	QL	11/18/2014	12/2/2014	IGTECO	2143-2014	12/17/2014	13630 LE	our site	1/8/2015	1/6/2015	Awaiting evaluation 6/12/2014 / Awaiting cheque to be ready. / Awaiting MRR and invoice received / Finished
MANS 38-15
MANS 39-15	15/11/2014	18/11/2014	Amira	18/11/2014	WINDSOCK	Q.L	30/11/2014	2/12/2014	GULF OIL SERVICES	2152/2014	21/12/2014	1750 L.E	MAIN OFFICE	9/1/2015	3/2/2015	* offers and samples sent to the field on 11/12/2014 for evaluation
MANS 40-15	15/11/2014	8/12/2014	Sally	8/12/2014	Spare parts for Solar turbines	Q.F.	9/12/2014	17/12/2014	APEX	3001/2015	12/1/2015	16309.28 USD	CFR	1/7/2015		items shipped 4/6 / items received at mansoura field without certificate of origin / email sent to vendor and their reply was sent to field / items were technically not accepted by memo dated 10/8 / fax sent to vendor and waiting for reply
MANS 41-15	15/11/2014	23/11/2014	Yasser	23/11/2014	GAS INJECTION PLANT AIR COOLER	Q.L.	12/1/2014	12/9/2014	SIE	2144/2014	12/11/2014	2,942.00 L.E.	Vendor place	4/22/2015		Partially received at head office.
MANS 42-15	18/11/2014	24/11/2014	Sally	24/11/2014	REFILLING HYDROGEN cylinder	QL			ULTRA PURE GAS	2134/2014	25/11/2014	450.00 L.E.	EX-W	9/12/2014	26/1/2015	memo sent to field to pick up the cylinder on 30/11/2014
MANS 43-15
MANS 44-15	14/12/2014	11/1/2015	Islam	11/1/2015	Check valves for for main manifold & sub manifold in gas injection plant	QF	1/11/2015	1/25/2015	MOSHIR	3009-2015	2/23/2015	7049 $	CFR	5/18/2015	6/20/2015	Awaiting delivery / Delivered,, Pending Payment
MANS 45-15	17/12/2014	25/12/2014	Sally	25/12/2014	Refillng nitrogen cylinder	QL			ULTRA PURE GAS	2155/2014	28/12/2014	1950.00 L.E.	EX-W	One week from receiving the empty cylinders	23/2/2015
MANS 46-15	19/12/2014	25/12/2014	Sally	25/12/2014	Refilling helium cylinder
MANS 47-15	26/12/2014	31/12/2014	Yasser	31/12/2014	PRE & post filter cartridge	Q.L.	1/5/2015	1/12/2015	Samiram	2003/2015	1/13/2015	26,250.00 L.E.	Cairo Head Office	1/20/2015	4/1/2015	Materials sent to fields on 15/01/2015 , Waiting final MRR.
MANS 48-15	27/12/2014	31/12/2014	Amira	31/12/2014	Spare parts for water return pumps	Q.F.	31/12/2014	8/1/2015	MOSHIR	3002/2015	12/1/2015	650 $	CPT Cairo Airport	13/4/2015	10/3/2015
MANS 49-15	30/12/2014	11/1/2015	Yasser	11/1/2015	Air ventilating fan	Q.L.	1/12/2015	1/15/2015	Electric & Future Home	2004/2015	1/15/2015	2,825.00 L.E.	Vendor place	1/22/2015	1/22/2015
MANS 50-15	1/1/2015	11/1/2015	Sally	11/1/2015	stationary	QL	23/3/2015	30/3/2015	AMERICAN GROUP	2033/2015	31/3/2015	12045.55 L.E.	HEAD OFFICE	8/4/2015	11/4/2015
					AL FAROUK	2033/2015 SUB1	31/3/2015	5159.08 L.E.	HEAD OFFICE	9/4/2015	11/4/2015	partially received at head office 5/4/2015
					BAKIER	2033/2015 SUB2	31/3/2015	2936.34 L.E.	HEAD OFFICE	12/4/2015	3/4/2015 (except item 5 & 6) / completed 7/5/2015	sent to mansoura field 5/4/2015 / remaining item sent to field 3/5 and waiting for MRR
MANS 51-15	1/1/2015	11/1/2015	Sally	11/1/2015	refilling zero air	QL	14/1/2015	19/1/2015 / EXT. 22/1/2015	UNI TRADE	2012/2015	3/2/2015	2500.00 L.E.	EX-W	19/2/2015	19/2/2015	offers sent to field for evaluation on 26/1/2015 / evaluation received 1/2 & calrification sent to vendor on 1/2
MANS 52-15	9/1/2015	19/1/2015	Mahmoud	19/1/2015	Belts for 1st stage E700A-B	QL	1/20/2015	2/15/2015	S.I.E	2010/2015	2/2/2015	3160 EGP	Vendor place	Once cheque is issued	2/24/2015	*Awaiting SIE to extend its offer / *Awaiting cheque to approved from finance since 2/2/2015 / *Awaiting MRR from Fields / *Finished
MANS 53-15	15/1/2015	18/2/2015	Tarek	18/2/2015	Spare parts for control panels of booster compressors	Q.F.	25-Feb-15	5-Mar-15	Tpcon	3016-2015	30-Mar-15	8,328 $	CPT Cairo Airport	15-Sep-15		* Waiting for technical evaluation from fields (Sent on 12-Mar-2015) / *P.O. issued and waiiting for supplier to submit L/G against advance payment / * New payment term is CAD through bank / * waiting delivery
MANS 54-15	22/1/2015	22/2/2015	Tarek	22/2/215	S.P.for areil compressors	Q.F.	3/8/2015	3/17/2015	Quimex	3026-2015	6/8/2015	21,681 $	CPT Cairo Airport	8/31/2015		* waiting for exterran to modify payment term rather than advance payment without L/G / * Under custom clearance and waiting for delivery from Airport to Site (23-August-2015)
MANS 55-15	26/1/2015	10/2/2015	Amira	10/2/2015	Spare parts for ESD valves	Q.F.	11/2/2015	18/2/2015 / 22/2/2015	WADICO	3010/2015	24/2/2015	GBP 3446.40	CPT Cairo Airport	28/4/2015	5/6/2015	* closing date extended up to 22/2/2015 / * UNDERS CUSTOMS PROCEDURES WITH THE ARABIAN COMPANY FROM 13/5/2015
MANS 56-15	16/1/2015	22/2/2015	Tarek	22/2/2015	Spare parts for caterplillar g3400	Q.F.			MANTRAC	3019-2015	7-May-15	110,907 $	CFR Alex Port	9/15/2015		* waiting for mantrac's offer / *Waiting for bid committee approval on direct order / * Items are pending at freezone due to payment delay
MANS 57-15
MANS 58-15	27/1/2015	22/2/2015	Tarek	22/2/2015	Spare parts for G3516 engines	Q.F.			MANTRAC	3019-2015	5/7/2015	110,907 $	CFR Alex Port	15-09-2015		* waiting for mantrac's offer / *Waiting for bid committee approval on direct order / * Items are pending at Cairo airport due to payment delay
MANS 59-15	27/1/2015	2/2/2015	Tarek	2/2/2015	Spare parts for G3500 engines	D.L.			MANTRAC	2016-2015	2/15/2015	22800 EGP	Mansoura site	2/23/2015	3/6/2015	* Waiting del
MANS 60-15	12/2/2015	22/2/2015	Sally	22/2/2015	Summer Coveralls	QL	22/2/2015	2/3/2015	MATTA	2036/2015	9/4/2015	94200.00 L.E.	Masoura field	20/6/2015	10/6/2015	Coveralls samples sent to field for evaluation dated 5/3/2015 / Evaluation received and calrification faxes sent to vendors on 12/3/2015 / samples sent to field and waiting for their evaluation / WAITING DELIVERY / *received at mansoura field 4/6 & waiting MRR
MANS 61-15
MANS 62-15
MANS 63-15	15/2/2015	5/3/2015	Islam	5/3/2015	Material for cathodic protection transformer	QL	3/5/2015	3/10/2015	Obeji	2028/2015	3/22/2015	3960 le	Vendor place	4/12/2015	4/12/2015	Awaiting quotations / Awaiting delivery / Awaiting MRR, Invoice received / Finished
MANS 64-15	16/2/2015	18/2/2015	Sally	18/2/2015	Refilling helium cylinder	QL			ULTRA PURE GAS	2019/2015	19/2/2015	1650.00 L.E.	EX-W	5/3/2015	5/4/2015	MEMO SENT TO FIELD ON 10/3/2015 TO PICK UP THE CYLINDER
MANS 65-15	16/2/2015	2/3/2015	Tarek	2/3/2015	Booster compressors engine spare parts	Q.F.					* waiting for Mantrac to confirm P/N / * D.O. is pending at Mr. Craig's office since june 2015 / * D.O. is approved by Mr. Craig and forwarded to Chairman's office for approval (02-Sep-2015)
MANS 66-15
MANS 67-15	21/2/2015	25/2/2015	Amira	25/2/2015	PPE		1/3/2015	8/3/2015	super supplies / sic	2044/2015 / 2044/2015 sub1	27/4/2015	10,080 l.e / 12,550 l.e	maadi office	30/5/2015 / 15/7/2015	8/7/2015	* offers sent to the field on 10/3/2015 for evaluation
MANS 68-15	28/2/2015	6/4/2015	Yasser	6/4/2015	Workshop consumable tools	Q.L.	4/8/2015	4/15/2015	El Hamad / El Wadi El Gedeed / Gulf Oil Ser. / IGS.	2080/2015SUB.01Rev.01 / 2080/2015Sub.03 / 2080/2015SUB.02 / 2080/2015	8/10/2015	962.00 L.E. / 8,060.00 L.E. / 2196.00 L.E. / 7,475.00 L.E.	Cairo Head Office	20-08-2015 / 13/09/2015 / 13/09/2015 / 17/08/2015		Offers Sent To Opr. For Evaluation
MANS 69-15	26/2/2015	8/3/2015	Yasser	8/3/2015	NEW TIRES FOR SOUTH BATRA FIELD CARS	Q.L.	3/8/2015	3/14/2015	Sabra Sons	2022/2015	3/15/2015	28,250.00 L.E.	Cairo Head Office	3/23/2015	3/24/2015	Waiting MRR.
MANS 70-15	28/2/2015	7/4/2015	Yasser	7/4/2015	Jax complete overhaul tools	Q.L.	4/8/2015	4/15/2015	El Hamad / El Wadi El Gedeed / Gulf Oil Ser. / IGS.	2079/2015Sub.01 / 2079/2015 / 2079/2015Sub.02 / 2079/2015Sub.03	8/9/2015	828.75 L.E. / 8,848.75 L.E. / 502.30 L.E. / 1,603.00 L.E.	Cairo Head Office	20-08-2015 / 13/09/2015 / 09/09/2015 / 17/08/2015		Offers sent to Opr. For Evaluation / Materials Sent to Fields and waiting final MRR.
MANS 71-15	6/3/2015	23/4/2015	Amira	23/4/2015	kitchen equip.	4/5/2015	11/5/2015		al qaswaa / international group	2059/2015 / 2059/2015 sub.1	1/6/2015	2736 / 2175	Vendor place		delivered
MANS 72-15	9/3/2015	15/3/2015	Sally	16/3/2015	Refilling Nitrogen cylinders	QL			ULTRA PURE GAS	2034/2015	5/4/2015	275.00 L.E.	EX-W	3/5/2015	12/5/2015	memo sent to field on 30-4 to pick up the cylinder from vendor's warehouse
MANS 73-15	12/3/2015	4/6/2015	Mahmoud	6/4/2015	battery for emergency light	QL	1/6/2015	1/6/2015	Rekabi (TRS)	2062/2015	14/6/2015	4250 L.E	HEAD OFFICE	7/7/2015	15/7/2015	*Awaiting offers / *Awaiting technical evaluation / *Awaiting delivery / *Viewtopia sent a battery for field subject to delivery which rejected by field on 25/04/2015 / * Supplier appologized for delivery and waiting new offers / *All seven new offers did not accepted technically on 12/05/2015 by feild / *Memo to field sent on 25/05/2015 for either to stick with the dimension or the Ampere / *Field sent a memo requesting the new dimension / *vendor offers sent to feild on 02/06/2015 for evaluation / *Awaiting delivery / *Finished
MANS 74-15	14/3/2015	19/3/2015	Tarek	19/3/2015	Add. Spare parts for dikirnis gas generator	QL	19-03-2015	22-03-2015	MANTRAC	2026/2015	22-03-2015	74,300 L.E.	Mantrac Mansoura Branch	01 -- Apr -2015	01 -- Apr-2015	* Waiting for offer
MANS 75-15	14/3/2015	6/4/2015	Tarek	6/4/2015	spare parts for air compressor	Q.F.	4/14/2015	23-04-2015	Atlas Copco	2050-2015	19-05-2015	2940 L.E.	Atlas copco Obour store	1 Week		* Waiting cheque issuance against delivery
					Ingersoll Rand	3022-2015	19-05-2015	7453 Euro	Ingersoll Rand	4 Weeks		*Waiting for fields technical evaluation (Sent on 30-apr-2015) / * waiting for delivery / * Items delivered at site and waiting for M.R.R.
MANS 76-15
MANS 77-15	21/3/2015	23/3/2015	Sally	23/3/2015	A4 PAPERS	QL	23/3/2015	30/3/2015	American Group	2033/2015	31/3/2015	12045.55 L.E.	HEAD OFFICE	8/4/2015	11/4/2015
MANS 78-15
MANS 79-15	27/3/2015	15/4/2015	Amira	15/4/2015	reflective traffic safety cones		22/4/2015	29/4/2015					8/7/2015	* I HAVE TWO OFFERS AND WAITING FOR ONE SAMPLE TO BE SEND TO THE FIELD FOE EVALUATION
MANS 80-15	28/3/2015	5-Apr-15	Mahmoud	5-Apr-15	Printings	Q.L	5-Apr-15	8-Apr-15	Macy Envelope	2037/2015 SUB.1	9-Apr-15	441 L.E.	HEAD OFFICE	21-Apr-15	19-Apr-15	*Awaiting offers / *Awaiting delivery / *Finished
					Fine Line	2037/2015 SUB.2	9-Apr-15	3111.50 L.E.	HEAD OFFICE	27-Apr-15	9-May-15
					Ray	2037/2015	9-Apr-15	2251 L.E.	HEAD OFFICE	27-Apr-15	23-Apr-15
MANS 81-15	30/3/2015	25/5/2015	Islam	26/5/2015	Isolation ball valves for suction scrubbers level transmitters in gas injection plant	QF	5/25/2015	6/9/2015	Petrozas	3029/2015	7/22/2015	1/6/1916	Free zone	10/21/2015		Awaiting quotations / Awaiting delivery
MANS 82-15
MANS 83-15
MANS 84-15	3/4/2015	6/7/2015	Tarek	7/7/2015	Spare parts for G3500 gas engine					* Waiting for supplier to extend offer validity (01-Sep-2015) / * Waiting for supplier to confirm P/N is compatible with the air starter motor
MANS 85-15	3/4/2015	6/4/2015	Tarek	7/4/2015	Spare parts for Bilqas deisel generator set					* Waiting offer / * waiting for direct order approval by 2 MDs (17-04-2015) / Delivered
MANS 86-15	5/4/2015	15/4/2015	Nehal	15/4/2015	TAMAD FIRE FIGHTING AURORA MAIN PUM	QF	16/4/2015	27/4/2015	APEX	3020/2015	18/05/2015	2/4/1906	CPT Cairo Airport	14/09/2015		* Waiting For Field Evaluation On 07/05/2015 / * Waiting for delivery / * Under Custom Clearance from 22/7/2015 / * Materials received at field & waiting for M.R.R.
MANS 87-15	7/4/2015	15/4/2015	Yasser	15/4/2015	Hand tools for well head maintenance	Q.L.	4/16/2015	4/25/2015	El Hamad	2052/2015	5/19/2015	8,896.00 L.E.	Cairo Head Office	5/31/2015		Offers sent to Opr. For Evaluation / Materials Sent to Fields and waiting final MRR.
MANS 88-15	9/4/2015	21/4/2015	Sally	21/4/2015	Refilling helium cylinder	QL			ULTRA PURE GAS	2040/2015	21/4/2015	1650.00 L.E.	EX-W	15 from receiving empty cylinder	11/6/2015	cylinder is ready at vendor's warehouse since 25/5 / waiting for the check to be ready at finance dept.
MANS 89-15	10/4/2015	21/4/2015	Islam	21/4/2015	V-belt for LPG S.Batra machinery	QF	4/21/2015	5/4/2015	ieco	2049/2015	5/14/2015	3494 le	Vendor place	5/28/2015	5/28/2015	Awaiting evaluation on 10/5/2015 / Awaiting delivery on 28/5/2015
MANS 90-15	10/4/2015	21/4/2015	Nehal	21/4/2015	Rotor tech glycol gear pumps for new model	QF	22/4/2015	28/4/2015	Colonial Harware	3024/2015	5/27/2015	$4,174.38	CIF Cairo air port	8/1/2015	25/8/2015	* Waiting For Field Evaluation On 07/05/2015 / * Waiting for vendor's reply for clarification / * Orders issued & waiting for delivery / * 3024/2015 Sub.1 is under custom clearance from 1/7/2015 / * 3024/2015 ( vendor adviced on 05/08/2015 that materials will be delivered to head office within 10 days)
					Techtools	3024/2015 Sub.1	5/27/2015	2,305.00 GBP	C&F cairo airport	8/6/2015	31/5/2015
MANS 91-15	11/4/2015	23/4/2015	Nehal	23/4/2015	Electrical spare parts for fire fighting plant	QF	27/4/2015	5/5/2015	Colonial Harware	3021/2015	18/05/2015	$1,817.65	CIF Cairo air port	21/09/2015		* Materials will be delivered to head office on 05/07/2015 / * Delivered
MANS 92-15	16/4/2015	3/5/2015	Yasser	3/5/2015	Diaphram pump	QF	5/11/2015	5/18/2015	Heliopower	2060/2015	6/2/2015	11,358.00 L.E.	Cairo Head Office	6/9/2015	6/10/2015
MANS 93-15	14/4/2015	10/6/2015	Tarek	15/6/2015	Alternator G					* Waiting for supplier to extend offer validity (01-Sep-2015)
MANS 94-15	17/4/2015	6/5/2015	Tarek	7/5/2015	Spare Parts For Engines of Khelala Diesel Generator					* waiting for fields technical evaluation (Sent 19-05-2015) / * D.O. is pending at Mr. Craig's office since june 2015 / * D.O. is approved by Mr. Craig and forwarded to Chairman's office for approval (02-Sep-2015)
MANS 95-15	20/4/2015	29/4/2015	Islam	30/4/2015	Manway gaskets	QF	4/30/2015	5/6/2015					Awaiting evaluation on 12/5/2015 / Awaiting fields advice for Napesco visit. / Awaiting correct description from Operations within the coming two weeks ends on 31/8/2015 and still no feedback
MANS 96-15	21/4/2015	25/5/2015	Yasser	26/5/2015	tools required for electrical dept. workshop	QF	5/31/2015	6/8/2015	RAF for trading	2085/2015	8/18/2015	7,545.00 L.E.	Vendor Store	9/27/2015		Offers Sent for evaluation dated
MANS 97-15
MANS 98-15
MANS 99-15	28/4/2015	3/5/2015	Islam	5/5/2015	Spare parts for haskel pump of wellhead control panel	QF	5/5/2015	5/11/2015	MOSHIR	2023-2015	5/31/2015	2955 $	CPT Cairo Airport	8/9/2015	8/8/2015	Awaiting quotations / Awaiting evaluation / Awaiting delivery / Under custom clearance
MANS 100-15	28/4/2015	3/5/2015	Sally	5/5/2015	stationary	QL	6/5/2015	13/5/2015	AL BARAKA	2055/2015	24/5/2015	12436.64 L.E.	HEAD OFFICE	4/6/2015	20/6/2015	received at head office will be sent to mansoura field / sent to field on 20/6 and waiting for MRR
					AL FAROUK	2055/2015SUB1	24/5/2015	1318.35 L.E.	HEAD OFFICE	8/6/2015	20/6/2015
					BAKIER	2055/2015SUB2	24/5/2015	1468.73 L.E.	HEAD OFFICE	7/6/2015	20/6/2015
MANS 101-15	5/5/2015	12/5/2015	Tarek	12/5/2015	Spare parts for G3500 engines					* Waiting for direct order approval by 2 MDs (sent 19-05-2015)
MANS 102-15	10/5/2015	18/5/2015	Tarek	20/5/2015	Starter motor for cat engine					* D.O. is pending at Mr. Craig's office since june 2015 / * D.O. is approved by Mr. Craig and forwarded to Chairman's office for approval (02-Sep-2015)
MANS 103-15	28/6/2015	22/7/2015	Amira	26/7/2015	coevralls & safety shoes
MANS 104-15	25/5/2015	1/6/2015	Nehal	4/6/2015	FIRE HYDRANT	QF / QL / QF	4/6/2015 / 25/6/2015 / 15/7/2015	15/6/2015 / 2/7/205 / 27/7/2015	NAFFCO	2078/2015	4/8/2015	20,520 L.E.	EX-W	9/12/2015		* Received offers are technically not accepted therefore new inquiry was sent for other vendors & with new closing date / * Waiting for delivery
					EL SAAD	2078/2015 SUB.1	4/8/2015	8,380 L.E.	EX-W	9/9/2015
MANS 105-15
MANS 106-15
MANS 107-15
MANS 108-15
MANS 109-15	23/5/2015	1/6/2015	Sally	2/6/2015	Refilling helium cylinder	QL			ULTRA PURE GAS	2061/2015	3/6/2015	1650.00 L.E.	EX-W	15 days from receiving the empty cylinder	10/7/2015	cylinder sent to vendor 17/6/2015 to refill
MANS 110-15
MANS 111-15	13/6/2015	7/17/2015	Yasser	7/18/2015	repair damage fences	Q.L.	7/21/2015	7/30/2015	El Tawheed / El Wadi El Gedeed	2086/2015 / 2086/2015Sub.01	8/20/2015	27,600.00 L.E. / 2,703.75 L.E.	Vendor place / Cairo H/O	8/31/2015		Offers Sent for Evaluation dated 03/08/2015
MANS 112-15	1/6/2015	18/6/2015	Amira	21/6/2015	Uniform
MANS 113-15	8/6/2015	14/6/2015	Amira	16/6/2015	Water finding paste
MANS 114-15	4/6/2015	8/6/2015	Tarek	9/6/2015	Khelala gas generator engine spare parts					Delivered
MANS 115-15	15/6/2015	1/7/2015	Sally	1/7/2015	Pillows & cotton bed sheets	QL					Samples sent to field for evaluation / *samples were technically not accepted / *other samples were sent to field on 9/8/2015 / *P.O.S UNDER PROCESS

EX-W :	Ex - Works
	M.R. Under Process

	Waiting for Delivery

	M.R. Completed

	M.R. is Cancelled, On Hold or Modified

	Tender

	M.R. wasn't received by Mat.Dept.

## MANS. ASST
Material Requests For Mansoura Asst.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
MANS ASST 1-15	1/7/14	2/11/14	Mahmoud	2/11/14	APC BACK -UPS	Q.L	11/3/2014	11/5/2014	NTG Egypt	2125/2014	11-Oct-14	1320 L.E	HEAD OFFICE	17-Nov-14	22-Nov-14	*Awaitng offers / *Awaiting technical evaluation / *Awaiting delivery / *Finished
MANS ASST 2-15					M.R. wasn't received by Mat.Dept.
MANS ASST 3-15	16/8/2014	2/11/14	Mahmoud	2/11/14	Electrical water heater	Q.L	11/3/2014	11/5/2014	Electric Center	2124/2014	6-Nov-14	670 L.E	Vendor Store	10-Nov-14	25-Nov-14	*Awaitig offers / *Awaiting delviery / *Finished
MANS ASST 4-15	15/9/2014	2/11/14	Sally	2/11/14	Computers	QL	3/11/2014	10/11/2014	CLICK	2128/2014 SUB1	19/11/2014	1710.00 L.E.	HEAD OFFICE	27/11/2014	5/12/2014	memo sent to field for evaluation & replied on 15/11/2014 / emails sent to vendors for calrification on 16/11/214 / items sent to field on 27/11/2014
					MICROTEC	2128/2014	19/11/2014	7550.00 L.E.	HEAD OFFICE	26/11/2014	15/12/2014
MANS ASST 5-15					M.R. wasn't received by Mat.Dept.
MANS ASST 6-15					M.R. wasn't received by Mat.Dept.
MANS ASST 7-15					M.R. wasn't received by Mat.Dept.
MANS ASST 8-15					M.R. wasn't received by Mat.Dept.
MANS ASST 9-15	17/9/2014	2/11/14	Amira	2/11/14	Gravity flow eyewash station	q.l	4/11/2014	11/11/2014 / 17/11/2014	SUPER SUPPLIES	2156/2014	31/12/2014	12000 L.E	MAADI OFFICE	1-Feb-15	25/1/2015	* the closing date extended up to 17/11/2014 because we have one offer only so we requoted on 12/11/2014 / * samples sent to the field for evaluation on 25/11/2014 / * EVALUATION RECEIVED FROM THE FIELD on 7/12/2014 with a comments so I sent it back to the vendor and waiting for their reply
MANS ASST 10-15					M.R. wasn't received by Mat.Dept.
MANS ASST 11-15					M.R. wasn't received by Mat.Dept.
MANS ASST 12-15					M.R. wasn't received by Mat.Dept.
MANS ASST 13-15	1/10/14	18/2/2015	Yasser	18/2/2015	Uninterruptible power supply	Q.L.	2/20/2015	2/24/2015	IEE.	2023/2015	16-Mar-15	17,556.00 L.E.	Vendor Store	23-Mar-15		Waiting MRR.
MANS ASST 14-15	8/10/14	13/1/2015	Amira	13/1/2015	Multi stage battery charger	q.f	14/1/2015	21/1/2015	moshir co.	3007/2015	4-Feb-15	$273	CPT CAIRO AIR PORT	9-Apr-15	1-May-15	* OFFERS SENT TO THE FIELD FOR EVALUATION ON 26/1/2015 / * received the field on 30/4/2015 and waiting for the receiving report
MANS ASST 15-15	14/10/2014	8/3/15	Tarek	8/3/15	Emission analyzer for caterpillar gas engine	Q.F	12/3/2015	25-03-2015	Tpcon	3018/2015	11-May-15	8127 Euro	CPT CAIRO AIR PORT	15-Sep-15		* Waiting offers / * waiting technical evaluation 01-apr-2015 / *reply received 15-Apr-2015 / *Clarification sent to suppliers 16-Apr-2015 / *suppliers replied 26-04-2015 / *Sent to field for confirmation / *Sent to supplier for confirming origin / *Waiting for suppliers to confirm (30-04-2015) / * Waiting delivery
MANS ASST 16-15	14/10/2014	13/1/2015	Yasser	13/1/2015	Power & hand tools for Khilala workshop	Q.F.	2/2/2015	2/18/2015	Apex / Al Moshir / Gulf Oil Services	3014/2015 / 2014/2015Sub.01 / 2025/2015	19-Mar-15	4,982.88 $ / 836.81 GBP / 6,105.00 L.E.	CPT CAIRO AIR PORT	05-07-2015 / 04/06/2015 / 21/04/2015
MANS ASST 17-15	26/2/2015	28/5/2015	Sally	2/6/15	Computers	Q.L.	10/6/2015	17/6/2015	COMPU ME	2066/2015	24/6/2015	10049.00 L.E.	HEAD OFFICE	9/7/2015 / 2/7/2015 / 6/8/2015	15-Jul-15	Offers sent for evaluation on 21/6/2015
					MICROTEC	2066/2015 SUB2	24/6/2015	780.00 L.E.	HEAD OFFICE	2/7/2015	9/7/2015
MANS ASST 18-15	30/10/2014	25/12/2014	Islam	25/12/2014	PCS UPGRADE	DF	12/28/2014	12/31/2014	Invensys	3076-2014	30-Dec-14	72496.86 $	free zone	24-May-15	24-May-15	Awaiting offer / Awaiting delivery / Awaiting MRR / Pending Payment / Finished
MANS ASST 19-15	18/11/2014	4/3/15	Tarek	4/3/15	Emission control system					Waiting offer / Waiting for mantrac to reply on clarification / Waiting for mantrac to confirm P/N / * Waiting for Mantrac to send revised offer (requested on 01-Sep-2015)
MANS ASST 20-15	21/11/2014	13/1/2015	Yasser	13/1/2015	Fiber glass hose cabinet	Q.L	1/18/2015	1/26/2015	El Wadi El Gedeed	2013/2015	3-Feb-15	19,500.00 L.E.	Cairo H/O	5-Mar-15	31-Mar-15
MANS ASST 21-15	26/2/2015	28/5/2015	Sally	2/6/15	printer	QL	10/6/2015	17/6/2015	INTERACT	2066/2015 SUB1	24/6/2015	3650.00 L.E.	HEAD OFFICE	9-Mar-15	7/7/2015	offers sent for evaluation on 21/6/2015
MANS ASST 22-15	2/12/14	13/1/2015	Mahmoud	13/1/2015	TVs	Q.L	1/14/2015	1/15/2015	Electric and Future Home	2006/2015	19-Jan-15	3850 EGP	Vendor Store	Upon Check Delivery	8-Feb-15	*Awaiting offers / *Awaiting techincal evaluation / *Awaiting cheque from finance since 19/Jan/2015 / *Cheque approved from fincane and TVs delivered at Head office on 29/01/2015 / *Finished
MANS ASST 23-15	8/12/14	13/1/2015	Mahmoud	13/1/2015	Electrical water heater	Q.L	1/14/2015	1/15/2015	Electric Center	2005/2015	19-Jan-15	1280 EGP	Vendor Store	Cash Upon Delivery	8-Feb-15	*Awaiting offers / *Awaiting delivery / *Finished
MANS ASST 24-15	11/12/14	13/1/2014	Yasser	13/1/2014	Mobile carbon dioxide fire extingishers	D.L.	1/13/2015	1/17/2015	Bavaria Egypt	2009/2015	26-Jan-15	34,880.00 L.E.	Mans. Fields	15-Mar-15	15-Mar-15	Waiting memo from HSE. Dept. "Field" for Direct Order from Bavaria.
MANS ASST 25-15					M.R. wasn't received by Mat.Dept.
MANS ASST 26-15	25/12/2014	12/1/15	Islam	12/1/15	Materials for network & cabling system for south batra site
MANS ASST 27-15	4/1/15	4/3/15	Islam	4/3/15	Diaphram pump for south mansoura plant	QL	3/4/2015	3/18/2015	Heliopower	2024-2015	19-Mar-15	10940 LE	MAADI OFFICE	26-Mar-15	27-Mar-15	Awaiting delivery / Finished
MANS ASST 28-15	26/2/2015	8/7/15	Sally	12/7/15	Scanner & printer				MICROTEC	2072/2015	15/7/2015	780.00 L.E.	HEAD OFFICE	29/7/2015		memo sent to IT dept on 13/7 / email sent to vendors to issue purchase orders ref to previous p.o.s / *order received 29/7 but is technically not accepted and waiting for vendor to replace it
					INTERACT	2076/2015	3/8/2015	2199.00 L.E.	HEAD OFFICE	13/8/2015	13/8/2015
					CLICK ITS	2076/2015SUB1	3/8/2015	2025.00 L.E.	HEAD OFFICE	13/8/2015		received at head office and will be sent to mansoura field
MANS ASST 29-15	21/1/2015	4/3/15	Amira	4/3/15	Electrical water heater	Q.L			ELECTRIC CENTER	2031/2015	31/3/2015	660 L.E	VENDOR STORE	4-Oct-15	12-Apr-15	* WAITING FOR THE CHEQUE / * sent to the field and waiting for receiving report
MANS ASST 30-15					M.R. wasn't received by Mat.Dept.
MANS ASST 31-15					M.R. wasn't received by Mat.Dept.
MANS ASST 32-15	7/4/15	25/5/2015	Islam	26/5/2015	Diaphram pumps for khilala and south mansoura	QF	5/25/2015	6/9/2015	Heliopower	2073/2015	22-Jul-15	37230 LE	Fields	5-Aug-15	5-Aug-15	Awaiting delivery / Awaiting invoice / Finished
MANS ASST 33-15	25/3/2015	26/4/2015	Yasser	26/4/2015	Tools needed for south batra workshop	Q.F.	4/28/2015	4/10/2015	Apex	3028/2015	12-Jul-15	3,580.52 $	CPT CAIRO AIR PORT	7-Oct-15		Offers sent to Mans. Fields for Evaluation dated 18/05/2015
MANS ASST 34-15					M.R. wasn't received by Mat.Dept.
MANS ASST 35-15	22/4/2015	28/4/2015	Yasser	28/4/2015	fire fighting system	Q.L.	4/29/2015	5/10/2015	Bavaria Egypt	2048/2015	14-May-15	25,020.00 L.E.	Mans. Fields	1-Jun-15	15-Jun-15
MANS ASST 36-15
MANS ASST 37-15
MANS ASST 38-15
MANS ASST 39-15
MANS ASST 40-15	10/5/2015	7/7/2015	Mahmoud	9/7/2015	Electrical battery charger for khilala plant	Q.L	12/7/2015	14/07/2015	Viewtopia	2074/2015	3-Aug-15	2340 EGP	HEAD OFFICE	19/08/2015	14-Aug-15	*Awaiting offers / *Awaiting evaluation / *Awaiting delivery

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## QANT
Material Requests For Qantara Field
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
QANT 01-15	25-Aug-14	3-Sep-14	Amira	3-Sep-14	Spare parts for qantara for Qantra instrument Air Compressor	Q.L.	17/9/2014	23/9/2014	FAC FILTER / المصرية الالمانية	2133/2014 / 2133/2014 SUB.1	24/11/2014	240.00 L.E / 762.00 L.E	VENDOR STORE	2 WEEKS	6-Jan-15	* on 8/9/2014 email sent to the field to provide us by a samples
Qant 02-15	25-Aug-14	3-Sep-14	Yasser	3-Sep-14	Tires	Q.L.	3-Sep-14	6-Sep-14	Sabra Sons	2102/2014	8-Sep-14	3,360.00 L.E.	Cairo Head Office	15-Sep-14	20-Sep-14	Tires Received And Sent To Qant. , Wainting Final Receiving
QANT 03-15	10-Oct-14	22/10/2014	Yasser	22/10/214	Lamps for Qantara equip. lighting system	Q.L.	25-Oct-14	30-Oct-14	El Swedy	2131/2014	23-Nov-14	2,520.00 L.E.	Cairo Head Office	7-Dec-14	5-Jan-15	Waiting final receiving from Qant. Fields.
QANT 04-15	17/12/2014	25/12/2014	Sally	25/12/2014	Electrical batteries	QL	28/12/2014	30/12/2014	BADRAN	2001/2015	1-Jan-15	3600.00 L.E.	EX-W	20/1/2015	23/1/2015	item received at head office 18/1/2015 & will be sent to mans field
QANT 05-15	2-May-15	7-May-15	Yasser	7-May-15	Lamps for Qantara equip. lighting system	Q.L.	5/31/2015	6/8/2015	Master Light	2071/2015	18-Aug-15	2100 EGP	VENDOR STORE	Upon cheque receiving	15/08/2015	*Awaiting offers / *Awaiting evaluation / *Awaiting delivery

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## ADMN
Material Requests For Adminstration Dept.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
ADMN 01-15	4-Aug-14	11-Aug-14	Sally	11-Aug-14	A4 PAPERS	QL	12-Aug-14	14-Aug-14	American group	2089/2014	17-Aug-14	29250.00 L.E.	Head Office	24-Aug-14	25-Aug-14
ADMN 02-15	21-Aug-14	26-Aug-14	Yasser	26-Aug-14	Mobile nokia	QL	26-Aug-14	29-Sep-14	I2	2096/2014	31-Aug-14	940.00 L.E.	Cairo Head Office	10-Sep-14	11-Sep-14
ADMN 03-15	21-Aug-14	26-Aug-14	Mahmoud	26-Aug-14	Marble washing machine	QL	31-Aug-14	1-Sep-14	Pro Team	2097/2014	1-Sep-14	425 L.E	Head Office	4-Sep-14	Not accepted technically	*Awaiting offers / *Awaititng evaluation / *PO no. 2097/2014 not accepted tecnichally / *Awaiting check to be issued by Finance Dept. since 30/09/2014 / *Finished
					Engineering Equipment Company	2110/2014	30-Sep-14	1375 L.E	Head Office	13-Oct-14	18-Oct-14
ADMN 04-15	21-Aug-14	26-Aug-14	Amira	26-Aug-14	Hp Toners	QL	27/8/2014	4-Sep-14	QUALITY	2101/2014 REV.1	7-Sep-14	20610 L.E	Head Office	20/9/2014	19/10/2014
ADMN 05-15	27-Aug-14	7-Sep-14	Amira	7-Sep-14	Uniform	q.l	23/9/2014	2-Oct-14	tie house	2119/2014	21/10/2014	l.e 38,910	vendor store	21/11/2014
ADMN 06-15	29/9/2014	13/10/2014	Mahmoud	14/10/2014	Printings	Q.L	14-Oct-14	16-Oct-14	ABAD AL WAHAB	2118/2014	20-Oct-14	1050 L.E	Head Office	30-Oct-14	2-Nov-14	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 07-15	29/9/2014	13/10/2014	Yasser	14/10/2014	Safety Shoes	D.L.	14-Oct-14	20-Oct-14	SSO.	2120/2014	23-Oct-14	2,800.00 L.E.	Cairo Head Office	9-Nov-14	15-Nov-14
ADMN 08-15	29/9/2014	14/10/2014	Mahmoud	14/10/2014	Charger for metal detector	purchased accoridng to supplier previous offer			safety and security consulting group	Paid cash from material treasury		300 L.E	Head Office	5-Nov-14	27-Nov-14	*Handheld metal detector is under maintenace / *Handheld metal detector will be replaced by another one, but waiting vendor to find another one / *Handheld metal detector replaced by another one and the charger received on 27/11/2014
ADMN 09-015	10-Sep-14	14/10/2014	Yasser	14/10/2014	tires	Q.L.	14-Oct-14	16-Oct-14	Sabra Sons	2117/2014	16-Oct-14	4,680.00 L.E.	Cairo Head Office	23-Oct-14	1-Nov-14
ADMN 10-15	20/10/2014	21/10/2014	Mahmoud	22/10/2014	Cartoon seperators	Q.L	26-Oct-14	27-Oct-14	ABAD AL WAHAB	2121/2014	29-Oct-14	525.00	Head Office	4-Nov-14	5-Nov-14	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 11-15	6/11/2014	9/11/2014	Mahmoud	10/11/2014	Annual Report	Q.L	11-Nov-14	12-Nov-14	RED ADVERTISING	2130/2014	30-Nov-14	14090.00	Head Office	10 Days after prova acceptance	8-Jun-15	*Awaiting offers / *Awaiting technical evaluation / *Awaiting soft copy with photos gallery from ADMN since 25/11/2014 / *Photos received from Admn Dept. on 9/12/2014 / *Awatiting soft copy prova from the supplier who receive the soft copy with photos on 10/12/2014 / *Awaiting first prova from supplier since 11/01/2015 (after acceptance of the design) / *Prova received by supplier on 26/01/2015 / *ADMN Dept. requested modifications from supplier on 15/2/2015 / *Supplier answered on 18/2/2015 / *Awaiting modifications from awarded supplier as requested from Admn. Dept on 27/04/2015 / *Final prova accepted from Admn dept. on 20/05/2015 / *Waiting the delivery / *Finished
ADMN 12-15	11/11/2014	17/11/2014	Sally	17/11/2014	Printings	QL	17/11/2014	20/11/2014	RAY	2132/2014	24/11/2014	3850.00 L.E.	Head Office	10/12/2014	12-Oct-14
ADMN 13-15	12/11/2014	17/11/2014	Islam	17/11/214	tires	QL	17-Nov-14	20-Nov-14	Tires home	2129-2014	20-Nov-14	6120 LE	Head office	27-Nov-14	27-Nov-14	Awaiting delivery / Finished
ADMN 14-15	17/11/2014	23/11/2014	Mahmoud	23/11/2014	Printings	Q.L	24-Nov-14	26-Nov-14	ABAD AL WAHAB	2137/2014	27-Nov-14	975 LE	Head Office	17-Dec-14	8-Dec-14	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 15-15
ADMN 16-15
ADMN 17-15	18/11/2014	23/11/2014	Islam	23/11/2014	Plastic roll	QL	23-Nov-14	24-Nov-14	bmoe	2135-2014	25-Nov-14	3240 LE	vendor place	16-Dec-14	16-Dec-14	Awaiting cheque to be ready / finished
ADMN 18-15	18/11/2014	23/11/2014	Mahmoud	23/11/2014	STAMPS	QL	24-Nov-14	26-Nov-14	RED ADVERTISING	2136/2014	2-Dec-14	436.36 LE	Head Office	1 Week from prova acceptance	11-Dec-14	*Awaiting offers / *Awaiting prova acceptance / *Finished
ADMN 19-15	20/11/2014	24/11/2014	Mahmoud	24/11/2014	Mobile nokia	Q.L	30-Nov-14	1-Dec-14	I2	2140/2014	2-Dec-14	818.18 L.E	Head Office	9-Dec-14	3-Dec-14	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 20-15	4/12/2014	7/12/2014	Yasser	7/12/2014	hood range	Q.L.	7-Dec-14	8-Dec-14	Electric Center	2141/2014	8-Dec-14	7,500.00 L.E.	vendor store	17-Dec-14	17-Dec-14
ADMN 21-15	4/12/2014	7/12/2014	Mahmoud	7/12/2014	Stationary	Q.L	7-Dec-14	9-Dec-14	BAKIER	2142/2014	8-Dec-14	800.91 L.E	Head Office	9-Dec-14	9-Dec-14	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 22-15	8/12/2014	14/12/2014	Amira	15/12/2014	Desk calender	Q.L	21/12/2014	22/12/2014	AL BARAKA	2153/2014	24/12/2014	2132 L.E	Head Office	30/12/2014	29/12/2014
ADMN 23-15	9/12/2014	14/12/2014	Amira	15/12/2014	Mobile	Q.L	21/12/2014	22/12/2014	RADWAN AL OGAIL	2154/2014	25/12/2014	1790 L.E	Head Office	30/12/2014	19/1/2015
ADMN 24-15	9/12/2014	14/12/2014	Yasser	15/12/2014	visitor cards	Q.L.	15-Dec-14	17-Dec-14	Integrated Design	2151/2014	21-Dec-14	625.00 L.E.	Cairo Head Office	8-Jan-15	22-Dec-14
ADMN 25-15	9/12/2014	14/12/2014	Sally	15/12/2014	Printings	QL			MACY	2149/2014	17/12/2014	1179.00 L.E.	Head Office	22/12/2014	21/12/2014	REF TO P.O. 2126/2014
ADMN 26-15	9/12/2014	14/12/2014	Yasser	15/12/2014	tires	Q.L.	15-Dec-14	17-Dec-14	El Motaheda for trade	2150/2014	21-Dec-14	5,400.00 L.E.	vendor store	31-Dec-14	31-Dec-14	Waiting final receiving from Admn. Dept.
ADMN 27-15	1/1/2015	8/1/2015	Yasser	11/1/2015	Printings	Q.L.	12-Jan-15	18-Jan-15	RAY Graphics / Bakier Stationery	2008/2015 / 2014/2015	20-01-2015 / 04/02/2015	1,285.00 L.E. / 480.00 L.E.	Cairo Head Office	01-02-2015 / 12/02/2015	01-02-2015 / 10/02/2015
ADMN 28-15	6/1/2015	28/1/2015	Mahmoud	28/1/2015	Mobile nokia	Q.L.	29-Jan-15	2-Feb-15	UNITED RETAIL CO. (I2)	2011/2015	2-Feb-15	475 L.E	Vedor Store	8-Feb-15	15-Feb-15	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 29-15	4/2/2015	11/2/2015	Sally	12/2/2015	Hp Toners	QL	12/2/2015	19/2/2015	Interact	2020/2015	24/2/2015	37782.00 L.E.	Head Office	Item 1,2,3,6,7,8: 4/3/2015 / item 4 & 5: 11/3/2015 / item 9,10,11,12: 22/4/2015	P/R 1/3/2015 / 2nd partial 2/4/2015 / completed 3/5/2015
					Quality	2020/2015 SUB1	24/2/2015	5580.00 L.E.	Head Office	8/3/2015	5/4/2015
ADMN 30-15	11/2/2015	25/2/2015	Amira	25/2/2015	Leather Bag	q.l	15/3/2015	18/3/2015	AL FAYOUMY	2032/2015	7-Apr-15	300 L.E	vendor store	8-Apr-15	DELIVERED
ADMN 31-15	16/3/2015	19/3/2015	Yasser	19/3/2015	tires	Q.L.	19-Mar-15	22-Mar-15	Sabra Sons	2027/2015	22-Mar-15	5,200.00 L.E.	Cairo Head Office	29-Mar-15	29-Mar-15
ADMN 32-15	16/3/2015	25/3/2015	Mahmoud	25/3/2015	PRINTINGS	Q.L.	25-Mar-15	26-Mar-15	ABAD AL WAHAB	2030/2015	15-Apr-15	258 L.E.	Head Office	15-Apr-15	15-Apr-15	*Waiting offers / *Waiting delivery / *Finished
ADMN 33-15	19/4/2015	21/4/2015	Mahmoud	21/4/2015	stamps	Q.L	21-Apr-15	22-Apr-15	RED ADVERTISING	2041/2015	23-Apr-15	804.55 L.E	Head Office	26-Apr-15	27-Apr-15	*Waiting offers / *Waiting delivery / *Finished
ADMN 34-15	29/3/2015	5/4/2015	Amira	5/4/2015	uniforms	q.l			tie house	2043/2015 / 2043/2015 rev.1	26/4/2015 / 3/5/2015	26640 l.e / 25,900 l.e	maddi office	30//5/2015 / 5/6/2015	5-Jul-15
ADMN 35-15	19/4/2015	23/4/2015	Sally	23/4/2015	A4 PAPERS	QL			American Group	2042/2015	23/4/2015	29750.00 L.E.	Head Office	30/4/2015	13/5/2015	REMINDER SENT TO VENDOR 5/5/2015 TO EXPIDITE THE DELIVERY
ADMN 36-15	23/4/2015	28/4/2015	Sally	28/4/2015	Stationary	QL	6/5/2015	13/5/2015	AL BARAKA	2054/2015	25/5/2015	24779.90 L.E.	Head Office	4/6/2015	8/6/2015	waiting for mansoura's stationary material request / field M.R. RECEIVED 6/5 / *p.o.s under process
					AL FAROUK	2054/2015SUB2	25/5/2015	4598.06 L.E.	Head Office	8/6/2015	9/6/2015
					BAKIER	2054/2015SUB1	25/5/2015	7032.28 L.E.	Head Office	7/6/2015	4/6/2015
ADMN 37-15	6/5/2015	10/5/2015	Mahmoud	10/5/2015	Printings	QL	13/05/2015	20/05/2015	MACY	2053/2015	25/05/2015	3930.45 EGP	Head Office	WITHIN 30 DAYS AFTER PROVA ACCEPTANCE	21-Jun-15	*Waiting offers / *Waiting delivery / *Finished
					AL FAROUK	2053/2015 SUB.1		1237.50 EGP		14 DAYS	3-Jun-15
					RAY	2053/2015 SUB.2		1820 EGP		14 DAYS AFTER PROVA ACCEPTANCE	10-June-15 / and / 21-June-15
					ABAD AL WAHAB	2053/2015 SUB.3		900 EGP		14 DAYS AFTER PROVA ACCEPTANCE	15-Jun-15
ADMN 38-15	10/5/2015	13/5/2015	Mahmoud	13/5/2015	Stainless baskets	Q.L	17/5/2015	18/05/2015	Engineering Equipment Company	2051/2015 Rev.1	2-Jun-15	2100 EGP	Vedor Store	Once cheque is issued form Finance Dept.	28-Jun-15	*Awaiting offers / *Materials received at head office on 25/05/2015 / *Memo from IT to change the size of the basket to be 20 liter instead of 5 liter (after delivery) in which adjusted size sent to same vendors for re-qutation on 25/05/2015 / *On 31/05/2015 Materials dept. sent memo to Admn dept. to raise the estimated cost which received from admn on 02/06/2015 / *Cheque memo sent to finance dept. on 02/06/2015 as per vendor request / *Awaiting delivery / *Finished
ADMN 39-15	21/5/2015	24/5/2015	Mahmoud	25/5/2015	Box Files	Q.L	13/05/2015	20/05/2015	AL FAROUK	2056/2015	28/05/2015	2475 EGP	Head Office	14 DAYS	3/6/2015	*Awaiting offers / *Awaiting delivery / *Finished
ADMN 40-15	9/6/2015	8/6/2015	Mahmoud	11/6/2015	bussiness cards	Q.L	15/06/2015	17/06/2015	Integrated Design	2065/2015	21/06/2015	682 EGP	Head Office	Within week after prova acceptance	23/08/2015	*Waiting offers / *Under prova / *Waiting delivery
ADMN 41-15	9/6/2015	11/6/2015	Mahmoud	11/6/2015	bridgestone tires	Q.L	15/06/2015	23/06/2015	المعادي للإطارات و البطاريات (عبده أمين)	2067/2015	28/06/2015	8440 EGP	Vedor Store	after cheque receiving	9/7/2015	*Waiting offers / *Waiting delivery
					شركة النيل للمشروعات	2067/2015 SUB.1		3168 EGP		5-Jul-15	2/8/2015
ADMN 42-15	10/6/2015	11/6/2015	Mahmoud	11/6/2015	travel bag	Q.L	14-Jun-15	18-Jun-15	الشركة المصرية السورية لصناعة الحقائب	2069/2015 Rev.1	30/07/2015	126,875 EGP	vendor store	Half quantitiy by max. 15/08/2015 and other half by max. 15/09/2015		*Waiting offers / *Waiting delivery
ADMN 43-15	15/6/2015	17/6/2015	Sally	18/6/2015	STAMPS	D.O.			ABAD EL WAHAB	2068/2015	25/6/2015	370.00 L.E.	Head Office	12/7/2015	13/7/2015	waiting for sample from vendor
ADMN 44-15	21/6/2015	23/6/2015	Mahmoud	28/6/2015	Carpet size 2m*3m	Q.L	1-Jul-15	1-Jul-15	Carpet City	2070/2015	6-Jul-15	1649.5 L.E.	Vendor Store	6-Jul-15	7-Jul-15	*Awaiting offers / *Awaiting evaluation / *Awaiting delivery / *Finished

Keys :	DDP :
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## ADMN ASST
Material Requests For Admn Asst
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
ADMN ASST 01-15	13-Jul-14	17-Jul-14	Islam	17-Jul-14	Softwares	Tender MAT 9-14
ADMN ASST 02-15	4-Aug-14	8-Sep-14	Sally	8-Sep-14	Computers, printers & UPS	QL	8-Sep-14	15-Sep-14	SOFT TREND	2106/2014	18-Oct-14	45000.00 L.E.	HEAD OFFICE	25-Sep-14	28-Sep-14
					QUALITY	2106/2014 SUB1	18-Oct-14	23530.00 L.E.	HEAD OFFICE	25-Sep-14	15/10/2014	waiting for the check to be ready
					NTG	2106/2014 SUB2	18-Oct-14	10,920.00 L.E.	HEAD OFFICE	25-Dec-14	2-Nov-14
					INTERACT	2106/2014 SUB3	18-Oct-14	8720.00 L.E.	HEAD OFFICE	16-Oct-14	25-Sep-14
ADMN ASST 3-15	23-Sep-14	28-Sep-14	Sally	28-Sep-14	Computers, & laptops	QL			SOFT TREND	2108/2014	29-Sep-14	61200.00 L.E.	HEAD OFFICE	2-Oct-14	cancelled	*email sent to three vendors to confirm their offer is still valid (admn asst 2-15) / *Vendors replied 28/9/2014 with confirmation
					HP MONITORS				QUALITY	2108/2014SUB1	26-Sep-14	7700.00 L.E.	HEAD OFFICE	9-Oct-14	16/10/2014
					UPS				NTG	2108/2014SUB2	26-Sep-14	5460.00 L.E.	HEAD OFFICE	30-Dec-14	2-Nov-14
					printers, workstation & ups		29-Sep-14	13-Oct-14	INTERACT	2114/2014	16/10/214	115770.00 L.E.	HEAD OFFICE	12-Nov-14	Partially received 29/10/2014 / completed 11/1/2015	*email sent to vendor to inform us the delivery of item no.2 & waiting for his reply
					printers & monitors				QUALITY	2114/2014SUB1	16/10/2014	10897.00 L.E.	HEAD OFFICE	22/10/2014	2-Nov-14
ADMN ASST 4-15	14/10/2014	20/10/2014	Islam	20/10/2014	printers & HW support
ADMN ASST 5-15	25/12/2014	11/1/2015	Islam	11/1/2015	printers	Q.L.	1/11/2015	1/11/2015	Interact	2002/2015	1/11/2015	24115 LE	Maadi	3/22/2015	3/17/2015	Awaiting delivery / Finished
ADMN ASST 6-15	3/2/2015	10/2/2015	Sally	10/2/2015	ID card printer	QL	12/2/2015	17/2/2015	SMART SYSTEM TECH	2018/2015	17/2/2015	9415.00 L.E.	HEAD OFFICE	24/2/2015	23/2/2015
ADMN ASST 7-15	11/2/2015	15/2/2015	Yasser	15/2/2015	furniture	Q.L.	2/16/2015	2/24/2015	El Wadi El Gedeed	2035/2015	4/5/2015	24,375.00 L.E.	Cairo H/O	5/12/2015	4/30/2015

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## OPR
Material Requests For Operations Dept.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
OPR 1-15	23/11/2014	21/12/2014	Tarek	21/12/2014	7" CASING	Tender
OPR 02-15	10/12/2014	25/12/2014	Yasser	25/12/2014	2 7/8" tubing coupling	Q.F.	12/25/2014	1/6/2015	Vallourec Oil & Gas France	3005/2015	1/20/2015	5,900.00 $	CPT Cairo Airport	3/9/2015	3/15/2015
OPR 3-15	16/3/2015	17/3/2015	Hussein	17/3/2015	Chemicals
OPR 4-15	3/6/2015	8/6/2015	Hussein	14/6/2015	Chemicals

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## PRJ
Material Requests For Projects Dept.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
PRJ 01-15	9-Jul-14	10-Jul-14	Tarek	10-Jul-14	EL-tamad Gas cap production project	Q.F.	15-Jul-14	22-Jul-14	SIGMA	3047-2014	30-Jul-14	17,420 $	Freezone	10 Days	* Delivered	Waiting del.
					GELDBACH	3047-2014 sub.1	30-Jul-14	2,192 $	Freezone	10 Days	* Delivered	Waiting del.
					TRANSAFRICA	3047-2014 sub.2	30-Jul-14	21,734 $	Freezone & CIF	10 Days and 1 Month for CIF	* Delivered	Waiting del. / * Under Custom clearance from 15-Sep-2014
PRJ 02-15	17-Jul-14	31-Jul-14	Tarek	3-Aug-14	El Tamad gas cap production project	Q.F.	4-Aug-13	11-Aug-14	Norriseal	3054-2014	8-Sep-14	9,885.15 $	CPT Cairo Airport	4-6 Wks from advance payment	* Delivered	* Waiting offers / * Waiting Advance payment to be transferred to vendor (24-sep-2014) / * Waiting Advance payment to be transferred to vendor (14-oct-2014) / * Under Custom clearance from 06-11-2014
PRJ 03-15
PRJ 04-15	3/12/2014	3/12/2014	Yasser	4/12/2014	insulation materials polythylene	Q.L.	12/4/2014	12/9/2014	Al Fagr Contractors	2145/2014	12/11/2014	33,750.00 L.E.	Mans. Fields	12/15/2014	12/15/2014	Waiting Final MRR.
PRJ 05-15	16/12/2014	17/12/2014	Yasser	17/12/2014	El tamad gas cap production project	Q.F.	12/21/2014	1/6/2015	TRANSAFRICA	3004/2015	1/15/2015	782.50 $	Alex. Free Zone	1/29/2015	2/2/2015
PRJ 06-15	4/2/2015	10/2/2015	Yasser	10/2/2015	Polyethylene 700 microns thickness	Q.L.	2/10/2015	2/15/2015	Al Fagr Contractors (F.C.O)	2015/2015	2/15/2015	13,500.00 L.E.	Mans. Fields	2/25/2015	2/25/2015
PRJ 07-15	15/1/2015	15/1/2015	Yasser	18/1/2015	Polyethylene 700 microns thickness	Q.L.	1/18/2015	1/20/2015	Al Fagr Contractors (F.C.O)	2007/2015	1/20/2015	20,250.00 L.E.	Mans. Fields	2/3/2015	2/4/2015	Del. Is Postbond according to Prj. Dept. Request
PRJ 08-15	1/4/2015	9/4/2015	Ahmed	9/4/2015	FIRE DETECTION AND ALARAM SYSTEM	Q.L.	28/4/2015	14/5/2015
PRJ 09-15	23/6/2015	2/7/2015	Yasser	6/7/2015	Prefab unit

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## IT.asst
Material Requests For IT Asst Dept.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
IT ASST 1-15	4-Jul-15	16/4/2015	Amira	19/4/2015	Plotter and inks	Q.L	22/4/2015	27/4/2015	INTERACT	2047/2015	3-May-15	56,435 L.E	HEAD OFFICE	20/7/2015
IT ASST 2-15	14/4/2015	16/4/2015	Sally	16/4/2015	Computers , UPS & scanner	QL	16/4/2015	23/4/2015	INTERACT	2045/2015	28/4/2015	62200.00 L.E.	HEAD OFFICE	28/7/2015	item 1: 13/7/2015
					SOURCE EGYPT	2045/2015 SUB1	28/4/2015	19767.00 L.E.	HEAD OFFICE	12/5/2015	19/5/2015
					MICROTEC	2045/2015 SUB2	28/4/2015	10240.00 L.E.	HEAD OFFICE	5/5/2015	6/5/2015

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.

## IT
Material Requests For IT Dept.
					2015

M.R. / NO.	M.R. / Date	M.R. / Received	Officer	Received by / Officer	Subject	Purchase / Method	Inquiry / Send Closing Date		Vendor	P.O. / NO.	P.O. / Date	P.O. / Value	Delivery / Terms	Promised / Delivery Date	Actual / Receiving Date	Remarks
IT 1-15	14/5/2015	19/5/2015	Sally	20/5/2015	HP toners	QL	20/5/2015	26/5/2015	INTERACT	2057/2015	6-Feb-15	21393.00 L.E.	Head Office	item 1-6: 11/8/2015 / item 7-11: 10/6/2015	8/6/2015

Keys :	DDP :	Delivery Duty Paid
	EX-W :	Ex - Works
		M.R. Under Process

		Waiting for Delivery

		M.R. Completed

		M.R. is Cancelled, On Hold or Modified

		Tender

		M.R. wasn't received by Mat.Dept.